# HEALTHWATCH RUTLAND ACTION LOG MARCH 2016 		PAPER B

| Item - Month raised | Date | Action agreed & by whom | Current status | Comments |
| --- | --- | --- | --- | --- |
| Ongoing -November 2015 | EMAS performance | Meeting held with EMAS December 2015 .Concern expressed by HWR that Rutland continued to be at the bottom of the access tables regionally partly due to ambulances tied up offloading at LRI. Agreed to hold an emergency services summit to work with the public to find specific solutions for Rutland. Collaborate in implementing new agreement | Gulnaz Katchi of EMAS to come back with proposals for " summit" in Spring of 2015 Pressure on the service has been unequalled over the winter with many breeches of targets as a result ( also at UHL A&E ) Support to " summit" given by EMAS Director of Operations. Meeting now scheduled for late spring . EMAS want Urgent Care Services involved . EMAS CEO has now stepped down and Director of Ops acting up. |  |
| 14.86 - Ongoing | SEND | Bring parent views on implementation back to Board Review periodically to chase progress | Jacqui Darlington asked to report back periodically as programme progresses |  |
| 14.87a | Governance policies | Put on website as refreshed | Website content and structure being reviewed + new website beuing commissioned |  |
| 14.88 - Ongoing | Cancer Targets | JF to pursue with CCG DH to putsue with UHL | City CCG has issued RAP notice & date given by UHL for compliance Some slight signs of improvement reported March 2016 |  |
| 14.87- Ongoing | Enter & View | Review progress after one year with Team Prepare forward programme | Forward programme agreed for 2016-17 |  |
| 14.87d | Dementia Project | Complete Pathway Mapping ( Hospital & End of Life) Complete Patient/carer interviews Complete Information section Prepare Interim report for RCC | Discussions held with HW Leicester City and UHL with a view to joint action Interviews ongoing Information Group not yet established First draft interim report prepared and will be finalised week beginning 21st March to be brought back to Board for sign off |  |
| 14.89 | Hard to reach groups | Include Men in groups to be targeted Make contact with hard to reach groups | Approach received from Men's Group November 2015 Followed up but no helpful contacts made . Agreed NFA and delete from Action Log |  |
| 15.7.10 | Minor Injuries | Contract awarded to N Doctors Arrangements to obtain public response to new contract agreed with CCG | Several more cases concerning interrelationship between Out of Hours/Urgent Care and111.Session held with representative of West Leicestershire CCG to pass on cases and concerns February 2016. |  |
| 15.7.11 | " We are Listening " | 2015-6 programme being finalised | 2015 programme completed November 2015 New arrangenments for 2016-17 ( including BCT) in draft Plan - on Agenda |  |
| 15.7.12 | Comms | Review membership and introduce double opt in system Website improvements | Membership reviewed Confidential distribution arrangements revised and implemented |  |
| 15.7.14 | Volunteers | Develop recruitment and support processes | Being gradually put in place as new recruits identified matching volunteer skills to work streams |  |
| 15.17.a | Volunteer Skills Audit | Due for completion by end March 2015 by ABS | Being carried out by Anya Loomes as she meets volunteers |  |
| 15.17.i | Recruitment of volunteers | Raise recruitment and profile raising | Two new volunteers have joined us since the last meting and a third has expressed an interest |  |
| 15.17.i | Schedule of meetings on website e | Finalise and publish meeting dates for 2016 | Formal meetings agreed Board on the Road to be finalised - Proposal to change format - see agenda |  |
| 15.18a Forward Plan | Ops Group for implementation | Start Planning for 2016-17 | Proposals worked up and brought to January 2016 Board Draft Plan and Budget on March agenda |  |
| 15.18.g | ARRVA | Survey patient experience | Collaboration with RCC total transport study and offer of assistance with survey from RCC. Survey underway |  |
| 15.65 | Dentistry | Await results of Oral Health survey Out of hours consultation | Additional practice ( 4 dentist) in Oakham about to go out to tender by NHS England The new practice will provide out of hours cover for Rutland There will be a reduction in capacity in Uppingham by December 2016 |  |
| 15.66e | Communications | Review arrangements | Recommendations being prepared for March Board |  |
| 15.69 | Draft Strategy for Community services | Send comments to CCG | Comments sent and included in Jan 2016 agenda |  |
| 15.70 | Young People's Mental Health | publicize £1/2m allocation when official | Problems over national allocation - see March agenda item |  |
| 15.72 | Better Care Together | Synchronise HWR listening with BCT consultation | Revised timetable awaited. Now not likely to be before June 23rd because of Referendum purdah |  |
| 15.73 | Policy - CQC | Agree modus vivendi with RCC re inspection/Enter & View visits to avoid overlap | Raised at contract monitoring |  |
| 16.11 | Young People's Mental Health | Showcase YPMH and other projects at Rutland Show | Book stand at Rutland Show on 5th June 2016 |  |